## Timeline
Project Timelines - HOT
Represents a milestone
|  | Sprint-1 (10 days) | Sprint 2 (10 days) | Sprint 3 (10 days) | Sprint 4 (10 days) | Sprint 5 (52 days) | Sprint 6 (10 days)
Activity | Dead Line | 07.03 - 21.03 | 22.03 - 04.04 | 05.04 - 18.04 | 19.04 - 03.05 | 04.05 - 17.07 | 18.07 - 31.07
Project Setup
Creating Git Repository
Creating Project in JIRA and Confluence
Setting up web Project and tech stack
Setting up Mobile Project in Android Studio and install libraries
Setting up CI for the Web project
Setup Developer Beta testing environmant on Android Play Store | 06.03.2017
Documentation
Project Schedule document
Software Requirements Specifications Document | 24.03.2017
Vision Scope + Risk List | 24.03.2017
UI Mockups (Web + Mobile)
Concluding on the Data sets to be used on the Project
Web
Map View
Filters
Visualisation blocks
Mobile
Filtering view
List view
Detail / Comparison View
Acceptance of UI Mockups by client | 04.04.2017
UI Prototypes (Web + Mobile)
Web
Map View
Filters
Visualisation blocks
Mobile
Filtering view
List view
Detail / Comparison View
Review Form
Acceptance of UI Prototypes by client | 18.04.2017
Mobile Application
Filtering view
List view
Detail / Comparison View
Review Form
Presentation of Mobile Application to Client | 29.04
Implementing changes from Presentation
Fied Testing
Implementing changes from the field testing
Acceptance of the Mobile Application by the client | 3.05
Web Application
Acquiring other data sets needed for the project
Querrying the OSMA API
Data Computations
Rendering computed data (Services and controllers)
Building views to display the computed data (Including Map layers)
Filtering and changing of parameters for a number and combination of datasource's
Data Visualisation
Presentation of Web Application to Client | 12.07
Implementing changes from Presentation
Acceptance of the Web Application by the client | 17.07
Deployment to Production
Deploying web app on Production environment | 20.07
Installing SSL Certificate | 20.07
Deploying Mobile app on Android Play Store | 20.07
Final Documentation
User manual
Support Contract
Delivery of final documentation | 28.07
Note on J7: kenneth kwesiga: May 01 is a public Holiday in Uganda known as Labor Day.
Note on L7: kenneth kwesiga: June 03 and 09 are celebrated public holidays in Uganda.
Note on N7: kenneth kwesiga: June 26 are celebrated public holidays in Uganda.
Note on I40: kenneth kwesiga: Invoice Client - 5,000 USD
Note on K50: kenneth kwesiga: Invoice Client - 9,000 USD
Note on M61: kenneth kwesiga: Invoice Client - 15,000 USD
Note on O69: kenneth kwesiga: Invoice Client - 5,000 USD